Autonomous Social Media Content Studio

5-Day Implementation Roadmap  |  Backend: LangGraph + FastAPI

Python  |  LangGraph  |  LangChain  |  Pydantic  |  FastAPI + Uvicorn  |  OpenAI / Anthropic     Effort: 5 days x 8 hrs = 40 hrs

# 1. Project at a Glance

One idea or blog goes in. A team of AI agents, led by a Content Manager, turns it into publish-ready LinkedIn, X and Instagram content. A Review Agent critiques the drafts and the weak ones are rewritten before the final package is returned.

| In scope: built in Days 1-5 | Designed for now, built later (not in the 5 days) |
| --- | --- |
| LangGraph workflow (state machine) Manager, LinkedIn, X, Instagram and Review agents Plan-Act-Check loop with reflection (max 2 revisions) FastAPI backend, error handling, optimization Tests, demo and documentation | Frontend: web UI that calls the same API Authentication: API key or JWT on the routes Observability: tracing, metrics, dashboards The architecture leaves clear plug-in points for these (see Section 6). |

# 2. System Architecture

Figure 1: Layered architecture. Solid boxes are built in 5 days; dashed boxes are future extensions.

How a request flows: Client sends the idea to POST /api/v1/generate. FastAPI validates it with Pydantic, runs the LangGraph workflow once, and returns the final content package. The graph is built once at startup and reused for every request.

# 3. Backend Folder Structure

| backend/ app/ main.py FastAPI app, startup config.py .env settings schemas.py Pydantic models llm.py model factory + retries api/routes.py /generate, /health prompts/ prompt text per agent tests/, docs/, .env.example, requirements.txt | graph/state.py GraphState graph/builder.py nodes + edges graph/routing.py approve / revise logic agents/manager.py plan + synthesize agents/linkedin.py platform agent agents/x.py platform agent agents/instagram.py platform agent agents/reviewer.py critique + score |
| --- | --- |

Each agent is its own module, so prompts, logic and tests stay separate. Auth, tracing and a frontend can be added later without changing the graph code.

# 4. Agent Workflow (State Machine)

Figure 2: LangGraph state machine following the Plan - Act - Check pattern with a revision loop.

| Agent / Node | Responsibility | Output (Pydantic model) |
| --- | --- | --- |
| Content Manager (Plan) | Reads the idea, audience and platforms. Builds one shared content brief (key message, tone, facts, call to action). | ContentBrief |
| LinkedIn Agent | Professional tone, strong first line, short paragraphs, 3-5 hashtags. Ideal length about 1,300 characters. | PlatformDraft |
| X Agent | Punchy and direct. Hard limit of 280 characters per post (checked in code); optional thread of up to 5 posts. | PlatformDraft |
| Instagram Agent | Friendly and visual tone, emojis, a clear call to action and relevant hashtags. | PlatformDraft |
| Review Agent (Check) | One call scores all drafts (1-10), lists issues, checks cross-platform consistency. A draft is approved at score 8 or above. | ReviewResult |
| Content Manager (Synthesize) | Decides: approve or send back. Assembles the final package in plain code (no extra LLM call). | FinalPackage |

Loop rule: if any draft is below the pass score, only those platforms are rewritten using the reviewer's feedback. The loop stops after 2 revisions, and any still-weak draft is returned with a warning, so the system can never loop forever.

# 5. Day-wise Implementation Plan

Each day ends with a working, testable result. Estimates assume 8 productive hours per day and include writing, running and fixing.

| DAY 1: Foundation, State Design and Graph Skeleton |  |  | 8 hrs |
| --- | --- | --- | --- |
| Goal: A runnable LangGraph with placeholder nodes and all data models defined. |  |  |  |
| # | Task | What to do (output) | Est. |
| 1 | Repo and environment setup | Create backend/ with venv, requirements.txt and .env.example (OPENAI_API_KEY, ANTHROPIC_API_KEY, MODEL_NAME, DEBUG_MODE). Load settings in config.py using dotenv. | 1 h |
| 2 | Roles and contracts | Finalize each agent's input, output and rules in a short docs/agents.md. This is the reference for later days. | 1 h |
| 3 | State and Pydantic models | Define GraphState, ContentBrief, PlatformDraft, ReviewResult, FinalPackage and the API request/response models. | 2 h |
| 4 | LLM client wrapper | llm.py with a get_llm() factory (OpenAI or Anthropic via MODEL_NAME), a structured-output helper, timeouts and retries. | 1.5 h |
| 5 | Graph skeleton | Add all nodes as stubs returning dummy data and wire the edges, including the conditional revise/approve edge. Run end to end from a local script. | 2 h |
| 6 | Logging and debug flag | Basic logging; DEBUG_MODE prints each node's input and output. | 0.5 h |
| Exit check: Local script runs START to END with dummy data; state diagram saved in docs/. |  |  |  |

| DAY 2: Manager Plan Node and Platform Agents |  |  | 8 hrs |
| --- | --- | --- | --- |
| Goal: Three platform agents produce quality drafts from a shared content brief. |  |  |  |
| # | Task | What to do (output) | Est. |
| 1 | Prompt design | Write a shared style guide plus one prompt per platform (tone, length, hashtags, call to action). Store in prompts/. | 1 h |
| 2 | Manager Plan node | Turns raw idea, blog or transcript into one ContentBrief (message, audience, tone, key facts). Created once and reused by all agents to avoid repeated work. | 1.5 h |
| 3 | LinkedIn Agent | Generate a structured PlatformDraft; add a length check in code. | 1.5 h |
| 4 | X Agent | Same pattern; code check that every post is within 280 characters, with thread support. | 1.5 h |
| 5 | Instagram Agent | Caption with emojis, hashtags and call to action; code check on hashtag count and length. | 1.5 h |
| 6 | Agent tests | Unit tests with a mocked LLM plus one manual run on a sample blog. | 1 h |
| Exit check: Sample blog returns three valid drafts that follow each platform's rules. |  |  |  |

| DAY 3: Review Agent, Reflection Loop and Manager Control |  |  | 8 hrs |
| --- | --- | --- | --- |
| Goal: The full Plan - Act - Check loop works with controlled revisions. |  |  |  |
| # | Task | What to do (output) | Est. |
| 1 | Review Agent | One call reviews all drafts: score 1-10, issues, suggestions, approved flag, plus a consistency check across platforms (same message and facts). | 2 h |
| 2 | Parallel fan-out and fan-in | Run the three platform agents in parallel using LangGraph's Send API; merge drafts into state with a reducer. | 1.5 h |
| 3 | Revision routing | Conditional edge: approve if all scores are at least 8, else route only the failed platforms back with feedback. Track revision_count; stop at MAX_REVISIONS = 2. | 2 h |
| 4 | Manager Synthesize node | Build FinalPackage: final posts, scores, revision history and any warnings. Pure code, no LLM call. | 1.5 h |
| 5 | Scenario testing | Test 3 inputs (long blog, short idea, transcript). Confirm the loop triggers, improves a weak draft and stops correctly. | 1 h |
| Exit check: A weak draft is rewritten once or twice, then the final package is returned. |  |  |  |

| DAY 4: FastAPI Backend, Error Handling and Optimization |  |  | 8 hrs |
| --- | --- | --- | --- |
| Goal: The workflow is available as a stable, tested API and runs efficiently. |  |  |  |
| # | Task | What to do (output) | Est. |
| 1 | FastAPI skeleton | main.py with routers, GET /health, CORS settings; compile the graph once at startup. | 1 h |
| 2 | Generate endpoint | POST /api/v1/generate: validate input (idea, audience, platforms, tone), run the graph, return the FinalPackage model. | 2 h |
| 3 | Error handling | Custom exceptions, retry with backoff on LLM failures, partial result with a warning if one agent fails, clear 4xx/5xx responses. | 1.5 h |
| 4 | Optimization pass | One shared brief, parallel agents, one batched review call, rewrite only failed platforms, max_tokens limits, optional cheaper model for review. Record llm_calls and latency in state. | 2 h |
| 5 | API tests | pytest with FastAPI TestClient and a mocked LLM for success, bad input and failure cases. | 1.5 h |
| Exit check: curl or Swagger UI call returns a full content package in a clean JSON format. |  |  |  |

| DAY 5: Testing, Demonstration and Documentation |  |  | 8 hrs |
| --- | --- | --- | --- |
| Goal: Verified system, demo ready and documentation complete as the single source of truth. |  |  |  |
| # | Task | What to do (output) | Est. |
| 1 | End-to-end testing | Run 4 real inputs (blog, idea, transcript, very short text) with the live LLM. Fix prompt and routing issues. | 1.5 h |
| 2 | Performance analysis | Compare before and after optimization: LLM calls, latency and tokens per request. | 1 h |
| 3 | Demonstration | Script showing multi-platform generation and one refinement example (draft, critique, improved draft). | 1.5 h |
| 4 | Architecture and design docs | Final diagrams, agent roles, delegation logic, reasoning flow and design trade-offs. | 2 h |
| 5 | README and cleanup | Setup steps, run commands, API examples; refactor, remove dead code, check error handling. | 1.5 h |
| 6 | Buffer | Reserved time for fixes found in testing. | 0.5 h |
| Exit check: A new person can set up, run and understand the project using only the README and docs. |  |  |  |

# 6. Ready for Extension (After Day 5)

| Capability | Where it plugs in | Already prepared in core |
| --- | --- | --- |
| Frontend | A web app calls POST /api/v1/generate and shows drafts and scores. | CORS enabled, stable response model, versioned /api/v1 path. |
| Authentication | A FastAPI dependency on the router (API key first, JWT later). | Routes grouped in one router so one dependency protects all. |
| Observability | LangSmith or Langfuse tracing passed through the graph run config; log shipping. | Logging module, request ID, and llm_calls / latency stored in state. |

# 7. Risks and Deliverable Mapping

| Risk | Mitigation |
| --- | --- |
| LLM returns badly formatted output | Use structured output with Pydantic and retry once on parse failure. |
| Endless revision loop or high cost | Hard cap of 2 revisions, max_tokens limits, rewrite only failed platforms. |
| Platform limits broken (e.g. X 280 characters) | Code-level validators run after generation, before review. |
| Schedule slips | Day 3 is the critical day. If late, move scenario testing into Day 5 buffer; keep optional extras out. |

| Project deliverable (from brief) | Delivered on |
| --- | --- |
| Functional multi-agent system with reflection loop | Days 2-3 |
| Architecture and workflow design (diagrams, delegation logic) | Day 1 draft, Day 5 final |
| Optimization, refactoring and error handling | Day 4 |
| Demonstration with iterative refinement example | Day 5 |
| Documentation (roles, workflow, trade-offs) | Day 5 |

Definition of done: all four agents plus manager run in one LangGraph; the revision loop works and stops at the limit; the API passes its tests; docs and demo are complete.